## Chandigarh
AWP&B 2017-18 Chandigarh
S.No. | Activity | Outlay Recommended for 2016-17 |  | Achievemnet upto 31.03.2017 from the funds received from GOI | Activity conducted in 2016-17 after taking loan of Rs. 23 crore | Total Achievement upto 31.03.17 |  |  |  | Outlay proposed for 2017-18 | [6 empty] | Outlay Recommended for 2017-18
[10 empty] | Spill Over including incurred liability of 2016-17 |  | Fresh |  |  | Total |  | Spill Over including incurred liability of 2016-17 |  | Deferred liability |  | Fresh |  |  | Total |  | Remarks
|  | Phy. | Fin. | Fin. | Fin. | Phy. | Fin. | Phy. (%) | Fin. (%) | Phy. | Fin. | Unit cost | Phy. | Fin. | Phy | Fin. | Phy. | Fin. | Phy. | Fin. | Unit Cost | Phy. | Fin. | Phy. | Fin.
I | ACCESS
SSA
1 | Opening of New Schools | [25 empty] | 0 | 1 | 1
1.01 | New Primary School | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
1.02 | Upgradation of PS to UPS | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
1.03 | Composite Schools | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
1.04 | Residential schools for specific category of children | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
1.05 | Residential Hostel | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
1.06 | Integration of Class V with primary schools | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
1.07 | Integration of Class VIII with upper primary schools | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2 | Residential Schools for specific category of children | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| 50 children | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Non-recurring (one time grant) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.01 | Furniture/ Equipment (including kitchen) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.02 | TLM and equipment including library books | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.03 | Bedding (new) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.04 | Replacement of bedding (once in 3 years) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total (Non Recurring) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Recurring (50 children) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.05 | Maintenance @ Rs.1,500/- per child Per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.06 | Stipend @ Rs.100/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.07 | Supplementary TLM, Stationery and other educational material @Rs.1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.08 | Salaries | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(a) | 1 Warden @ Rs.25,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(b) | 4 Fulltime teachers as per RTE Norms @ Rs. 20,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(c) | 2 Urdu Teachers (only for Blocks with muslim population above 20% and select urban areas) if required @ Rs.12,000/- per month per teacher. | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(d) | 3 Part time teachers @ Rs.5,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(e) | 1 Full time Accountant @ Rs. 10,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(f) | 2 Support staff - (Accountant/Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(g) | 1 Head Cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.09 | Specific Skill training @ Rs.1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.1 | Electricity / water charges @ Rs. 1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.11 | Medical care/contingencies @ Rs.1,250/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.12 | Maintenance @ Rs. 750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.13 | Miscellaneous @ Rs. 750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.14 | Preparatory camps @ Rs. 300/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.15 | P.T.A / school functions @ Rs. 300/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.16 | Provision of Rent @ Rs. 10,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.17 | Capacity Building @ Rs. 500/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.18 | Physical / Self Defence Training @ Rs.200/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total (Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Total (Non Recurring + Recurring) | [25 empty] | 0 | 1 | 1
| 100 children | [25 empty] | 0 | 1 | 1
| Non-recurring (one time grant) | [25 empty] | 0 | 1 | 1
2.19 | Furniture / Equipment (including kitchen equipment) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.2 | TLM and equipment including library books (New) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.21 | Bedding (New) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.22 | Replacement of bedding (once in 3 years) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total Non-recurring | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Recurring | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.23 | Maintenance @ Rs. 1,500/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.24 | Stipend @ Rs.100/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.25 | Supplementary TLM, Stationery and other educational material @1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.26 | Salaries | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(a) | 1 Warden @ Rs. 25,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(b) | 1 head teacher @ Rs. 25,000/- per month in case the enrollment exceeds 100 | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(c) | 4 - 5 Full time teachers as per RTE norms @ Rs. 20,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(d) | 2 Urdu Teachers (only for blocks with muslim population above 20% and select urban areas), if required @ Rs. 12,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(e) | 3 part time teachers @ Rs. 5,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(f) | 1 Full time Accountant @ Rs. 10,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(g) | 2 Support Staff – (Accountant/ Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(h) | 1 Head cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.27 | Specific skill training @ Rs. 1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.28 | Electricity / water charges @Rs. 1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.29 | Medical care/contingencies @ Rs. 1,250/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.3 | Maintenance @ Rs. 750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.31 | Miscellaneous @ Rs. 750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.32 | Preparatory camps @ Rs.200/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.33 | P.T.A / school functions @ Rs.200/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.34 | Provision of Rent @ Rs. 6,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.35 | Capacity Building @ Rs. 500/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
2.36 | Physical / Self Defence training @ Rs. 200/- per child per annum. | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total (Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Total (Recurring + Non Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Total (50 + 100 children) | [25 empty] | 0 | 1 | 1
3 | Residential Hostel for specific category of children | [25 empty] | 0 | 1 | 1
(A) | 50 children | [25 empty] | 0 | 1 | 1
| Non-recurring (one time grant) | [25 empty] | 0 | 1 | 1
3.01 | Furniture/ Equipment (including kitchen) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.02 | TLM and equipment including library books | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.03 | Bedding (new) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.04 | Replacement of bedding (once in 3 years) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total (Non Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Recurring (50 children) | [25 empty] | 0 | 1 | 1
3.05 | Maintenance @ Rs.1,500/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.06 | Stipend @ Rs.100/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.07 | Supplementary TLM, Stationery and other educational material @Rs.1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.08 | Salaries | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(a) | 1 Warden @ Rs. 25,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(b) | 4 Fulltime teachers as per RTE Norms @ Rs. 20,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(c) | 2 Urdu Teachers (only for Blocks with muslim population above 20% and select urban areas) if required @ Rs.12,000/- per month per teacher. | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(d) | 3 Part time teachers @ Rs.5,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(e) | 1 Full time Accountant @ Rs. 10,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(f) | 2 Support staff - (Accountant/Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(g) | 1 Head Cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.09 | Specific Skill training @ Rs.1000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.1 | Electricity / water charges @ Rs. 1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.11 | Medical care/contingencies @ Rs.1,250/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.12 | Maintenance @ Rs. 750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.13 | Miscellaneous @ Rs. 750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.14 | Preparatory camps @ Rs. 300/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.15 | P.T.A / school functions @ Rs. 300/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.16 | Provision of Rent @ Rs. 10,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.17 | Capacity Building @ Rs. 500/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.18 | Physical / Self Defence Training @ Rs.200/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total (Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Total (Non Recurring + Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
(B) | 100 Children | [25 empty] | 0 | 1 | 1
| Non-recurring (one time grant) | [25 empty] | 0 | 1 | 1
3.19 | Furniture / Equipment (including kitchen equipment) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.2 | TLM and equipment including library books (New) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.21 | Bedding (New) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.22 | Replacement of bedding (once in 3 years) | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total Non-recurring | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Recurring | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.23 | Maintenance @ Rs. 1,500/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.24 | Stipend @ Rs.100/- per child per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.25 | Supplementary TLM, Stationery and other educational material @1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.26 | Salaries | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(a) | 1 Warden @ Rs. 25,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(b) | 1 head teacher @ Rs. 25,000/- per month in case the enrollment exceeds 100 | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(c) | 4 - 5 Full time teachers as per RTE norms @ Rs. 20,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(d) | 2 Urdu Teachers (only for blocks with muslim population above 20% and select urban areas), if required @ Rs. 12,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(e) | 3 part time teachers @ Rs. 5,000/- per month per teacher | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(f) | 1 Full time Accountant @ Rs. 10,000/- per month | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(g) | 2 Support Staff – (Accountant/ Assistant, Peon, Chowkidar) @ Rs. 5,000/- per month per staff | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
(h) | 1 Head cook @ Rs. 6,000/- per month and upto 2 Asstt. Cooks @ Rs. 4,500/- per month per cook | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.27 | Specific skill training @ Rs.1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.28 | Electricity / water charges @ Rs.1,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.29 | Medical care/contingencies @ Rs.1,250/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.3 | Maintenance @ Rs.750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.31 | Miscellaneous @ Rs.750/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.32 | Preparatory camps @ Rs.200/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.33 | P.T.A / school functions @ Rs.200/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.34 | Provision of Rent @ Rs. 6,000/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.35 | Capacity Building @ Rs.500/- per child per annum | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
3.36 | Physical / Self Defence training @ Rs. 200/- per child per annum. | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total (Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Total (Recurring + Non Recurring) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
| Total (A + B) | [22 empty] | 0 | 0 |  | 0 | 1 | 1
4 | Transport/Escort Facility | [25 empty] | 0 | 1 | 1
4.01 | Children in remote habitation | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
4.02 | Urban deprived children/children without adult protection | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | [21 empty] | 0 | 0 | 0 |  |  | 1 | 1
5 | Reimbursement of Fee against 25% admission under Section 12(1)(c) of RTE Act 2009 (Entry Level) subject to upper limit of 20% of AWP&B guidelines issued by MHRD | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | [21 empty] | 0 | 0 | 0 |  |  | 1 | 1
6 | Special Training for mainstreaming of out of school children | [25 empty] | 0 | 1 | 1
6.01 | Residential (Fresh) | [25 empty] | 0 | 1 | 1
| (a) 12 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) 9 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| (c) 6 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| (d) 3 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | [21 empty] | 0 | 0 | 0 |  |  | 1 | 1
6.02 | Residential (Continuing from previous year) | [25 empty] | 0 | 1 | 1
| (a) 12 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) 9 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| (c) 6 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| (d) 3 months | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | [21 empty] | 0 | 0 | 0 |  | 0 | 1 | 1
6.03 | Non-Residential (Fresh) | [25 empty] | 0 | 1 | 1
| (a) 12 months | 2471 | 148.26 | 98.27 | 47.11 | 2471 | 145.38 | 100 | 98.0575 |  | 47.11 | 0.06 | 2629 | 157.74 | 2629 | 204.85 | 0 | 47.11 |  |  | 0.06 | 2629 | 157.74 | 2629 | 204.85 | Recommended as proposed | 204.85 | 1 | 1
| (b) 9 months | 546 | 24.57 | 18.55 | 4.02 | 546 | 22.57 | 100 | 91.86 |  | 4.02 | 0.045 | 299 | 13.455 | 299 | 17.475 | 0 | 4.02 |  |  | 0.045 | 299 | 13.455 | 299 | 17.475 |  | 17.475 | 1 | 1
| (c) 6 months | 444 | 13.32 | 9.74 | 2.46 | 444 | 12.2 | 100 | 91.5916 |  | 2.46 | 0.03 | 274 | 8.22 | 274 | 10.68 | 0 | 2.46 |  |  | 0.03 | 274 | 8.22 | 274 | 10.68 |  | 10.68 | 1 | 1
| (d) 3 months |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 3461 | 186.15 | 126.56 | 53.59 | 3461 | 180.15 | 100 | 96.7768 |  | 53.59 | 0.135 | 3202 | 179.415 | 3202 | 233.005 | 0 | 53.59 |  |  | 0.135 | 3202 | 179.415 | 3202 | 233.005 |  |  | 1
6.04 | Non-Residential (Continuing from previous year) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) 12 months | 628 | 37.68 | 26.32 | 9.18 | 628 | 35.5 | 100 | 94.2144 |  | 9.18 | 0.06 | 512 | 30.72 | 512 | 39.9 | 0 | 9.18 |  |  | 0.06 | 512 | 30.72 | 512 | 39.9 | Recommended as proposed | 39.9 | 1 | 1
| (b) 9 months | 250 | 11.25 | 6.09 | 4.48 | 250 | 10.57 | 100 | 93.9556 |  | 4.48 | 0.045 | 333 | 14.985 | 333 | 19.465 | 0 | 4.48 |  |  | 0.045 | 333 | 14.985 | 333 | 19.465 |  | 19.465 | 1 | 1
| (c) 6 months | 349 | 10.47 | 7.27 | 2.3 | 349 | 9.57 | 100 | 91.404 |  | 2.3 | 0.03 | 257 | 7.71 | 257 | 10.01 | 0 | 2.3 |  |  | 0.03 | 257 | 7.71 | 257 | 10.01 |  | 10.01 | 1 | 1
| (d) 3 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 1227 | 59.4 | 39.68 | 15.96 | 1227 | 55.64 | 100 | 93.67 |  | 15.96 | 0.135 | 1102 | 53.415 | 1102 | 69.375 | 0 | 15.96 |  |  |  | 1102 | 53.415 | 1102 | 69.375 |  |  | 1
6.05 | Madarasa/Maktab |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) 12 months | 422 | 25.32 | 17.2 | 7.44 | 352 | 24.64 | 83.4123 | 97.3144 |  | 7.44 | 0.06 | 414 | 24.84 | 414 | 32.28 | 0 | 7.44 |  |  | 0.06 | 220 | 13.2 | 220 | 20.64 | Recommended as appraised. Includes 124 continuing and 96 Fresh @ of Rs. 0.06 lakh each | 20.64 | 1 | 1
| (b) 9 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1 | 13.2
| (c) 6 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (d) 3 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 422 | 25.32 | 17.2 | 7.44 | 352 | 24.64 | 83.4123 | 97.3144 |  | 7.44 | 0.06 | 414 | 24.84 | 414 | 32.28 | 0 | 7.44 |  |  | 0.06 | 220 | 13.2 | 220 | 20.64 |  |  | 1 | 1
6.06 | Seasonal Hostel (Residential) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) 12 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (b) 9 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (c) 6 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (d) 3 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| Sub Total |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [9 empty] | 1 | 1
6.07 | Seasonal Hostel (Non Residential) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) 12 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (b) 9 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (c) 6 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (d) 3 months |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| Sub Total |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
1 | Total | 5110 | 270.87 | 183.44 | 76.99 | 5040 | 260.43 | 98.6301 | 96.1458 |  | 76.99 | 0.33 | 4718 | 257.67 | 4718 | 334.66 | 0 | 76.99 |  |  | 0.33 | 4524 | 246.03 | 4524 | 323.02 |  |  | 1
II | RETENTION |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
7 | Free Text Books |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
7.01 | Free Text Books (P) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) Class I & II | 20409 | 30.6137 | 0.00367 | 30.61 | 20409 | 30.6137 | 100 | 100 |  | 30.61 | 0.0015 | 19809 | 29.7135 | 19809 | 60.3235 | 0 | 30.61 |  |  | 0.0015 | 19809 | 29.7135 | 19809 | 60.3235 | Recommended as proposed | 60.3235 | 1 | 1
| (b) Braille Books Class I & II |  |  | 0 | [6 empty] | 0 | 0.0015 | 2 | 0.003 | 2 | 0.003 | 0 | 0 |  |  | 0.0015 | 2 | 0.003 | 2 | 0.003 | Recommended as proposed | 0.003 | 1 | 1
| (c) Large Print Books Class I & II | 2 | 0.003 | 0 |  |  |  | 0 | 0 |  | 0 | 0.0015 | 2 | 0.003 | 2 | 0.003 | 0 | 0 |  |  | 0.0015 | 2 | 0.003 | 2 | 0.003 | Recommended as proposed | 0.003 | 1 | 1
| (d) Class III to V | 41174 | 61.7613 | 0.00133 | 61.76 | 41174 | 61.7613 | 100 | 100 |  | 61.76 | 0.0015 | 40416 | 60.624 | 40416 | 122.384 | 0 | 61.76 |  |  | 0.0015 | 40416 | 60.624 | 40416 | 122.384 | Recommended as proposed | 122.384 | 1 | 1
| (e) Braille Books Class III to V | 4 | 0.006 | 0 |  |  |  | 0 | 0 |  | 0 | 0.0015 | 1 | 0.0015 | 1 | 0.0015 | 0 | 0 |  |  | 0.0015 | 1 | 0.0015 | 1 | 0.0015 | Recommended as proposed | 0.0015 | 1 | 1
| (f) Large Print Books Class III to V | 30 | 0.045 | 0 |  |  |  | 0 | 0 |  | 0 | 0.0015 | 24 | 0.036 | 24 | 0.036 | 0 | 0 |  |  | 0.0015 | 24 | 0.036 | 24 | 0.036 | Recommended as proposed | 0.036 | 1 | 1
7.02 | Free Text Books (UP) | 46956 | 117.39 | 0 | 117.39 | 46956 | 117.39 | 100 | 100 |  | 117.39 | 0.0025 | 46858 | 117.145 | 46858 | 234.535 | 0 | 117.39 |  |  | 0.0025 | 46858 | 117.145 | 46858 | 234.535 | Recommended as proposed | 234.535 | 1 | 1
7.03 | Braille Books (UP) | 1 | 0.0025 | 0 |  |  |  | 0 | 0 |  | 0 | 0.0025 | 2 | 0.005 | 2 | 0.005 | 0 | 0 |  |  | 0.0025 | 2 | 0.005 | 2 | 0.005 | Recommended as proposed | 0.005 | 1 | 1
7.04 | Large Print Books (UP) | 55 | 0.1375 | 0 |  |  |  | 0 | 0 |  | 0 | 0.0025 | 54 | 0.135 | 54 | 0.135 | 0 | 0 |  |  | 0.0025 | 54 | 0.135 | 54 | 0.135 | Recommended as proposed | 0.135 | 1 | 1
2 | Sub Total | 108631 | 209.959 | 0.005 | 209.76 | 108539 | 209.765 | 99.9153 | 99.9076 |  | 209.76 | 0.0165 | 107168 | 207.666 | 107168 | 417.426 | 0 | 209.76 |  |  | 0.0165 | 107168 | 207.666 | 107168 | 417.426 |  |  | 1
8 | Provision of 2 sets of Uniform |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | Recommended as proposed | 0 | 1 | 1
8.01 | All Girls |  |  | 0 | [6 empty] | 0 | 0.0035 | 45692 | 159.922 | 45692 | 159.922 | 0 | 0 |  |  | 0.004 | 45692 | 182.768 | 45692 | 182.768 |  | 182.768 | 1 | 1
8.02 | SC Boys |  |  | 0 | [6 empty] | 0 | 0.0035 | 5803 | 20.3105 | 5803 | 20.3105 | 0 | 0 |  |  | 0.004 | 5803 | 23.212 | 5803 | 23.212 |  | 23.212 | 1 | 1
8.03 | ST Boys |  |  | 0 | [6 empty] | 0 | 0.0035 | 19 | 0.0665 | 19 | 0.0665 | 0 | 0 |  |  | 0.004 | 19 | 0.076 | 19 | 0.076 |  | 0.076 | 1 | 1
8.04 | BPL Boys |  |  | 0 | [6 empty] | 0 | 0.0035 | 1076 | 3.766 | 1076 | 3.766 | 0 | 0 |  |  | 0.004 | 1076 | 4.304 | 1076 | 4.304 |  | 4.304 | 1 | 1
| Sub Total |  |  | 0 | [6 empty] | 0 | 0.0035 | 52590 | 184.065 | 52590 | 184.065 | 0 | 0 |  |  |  | 52590 | 210.36 | 52590 | 210.36 |  |  | 1
9 | Teaching Learning Equipment (TLE) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
9.01 | New Primary |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
9.02 | New Upper Primary |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
III | ENHANCING QUALITY |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
10 | New Teachers' Salary |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
| Primary Teachers |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
10.01 | New Primary Teachers (Regular) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.02 | New Primary Teachers (Contractual) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.03 | Head Teachers for Primary (if the number of children exceeds 150 in a school) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Upper Primary Teachers |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.04 | Subject specific New Upper Primary Teachers (Regular) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Science and Mathematics |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) Social Studies |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (c) Languages |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.05 | Subject specific New Upper Primary Teachers (Contractual) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Science and Mathematics |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) Social Studies |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (c) Languages |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.06 | Head Teachers for Upper Primary (if the number of children exceeds 100 in a school) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.07 | Part Time Instructors (if the number of children exceeds 100 in a school) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Art Education |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) Health and Physical Education |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (c) Work Education |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 1 | 1
| Total |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 1 | 1
| Teachers' Salary (Recurring-sanctioned earlier) in position |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Primary Teachers |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.08 | Primary Teachers - Existing, in position (Regular) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.09 | (a) Primary Teachers - Existing, in position (Contractual) committed liability | 540 | 2592 | 1472.623 | 918.94 | 516 | 2391.563 | 95.5556 | 92.2671 |  | 918.94 | 0.44 | 728 | 3284.16 | 728 | 4203.1 | 0 | 918.94 |  |  | 0.44 | 516 | 2724.48 | 516 | 3643.42 | Recommended as appriased | 3643.42 | 1 | 1
10.1 | Head Teachers for Primary in position |  |  | 0 | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Upper Primary Teachers |  |  | 0 | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.11 | Subject Specific Upper Primary Teachers- in position (Regular) |  |  | 0 | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Science and Mathematics |  |  | 0 | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) Social Studies |  |  | 0 | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (c) Languages |  |  | 0 | [6 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
10.12 | Subject Specific Upper Primary Teachers - in position (Contractual) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| (a) Science and Mathematics | 190 | 1026 | 596.68 | 378.31 | 189 | 974.99 | 99.4737 | 95.0283 |  | 378.31 | 0.5 | 246 | 1305 | 246 | 1683.31 | 0 | 378.31 |  |  | 0.495 | 189 | 1122.66 | 189 | 1500.97 | Recommended as appraised with 10% increment | 1500.97 | 1 | 1
| (b) Social Studies | 117 | 631.8 | 330.3 | 222.84 | 115 | 553.14 | 98.2906 | 87.5499 |  | 222.84 | 0.5 | 152 | 801 | 152 | 1023.84 | 0 | 222.84 |  |  | 0.495 | 115 | 683.1 | 115 | 905.94 |  | 905.94 | 1 | 1
| (c) Languages | 182 | 982.8 | 564.92 | 352.49 | 176 | 917.41 | 96.7033 | 93.3466 |  | 352.49 | 0.5 | 249 | 1275 | 249 | 1627.49 | 0 | 352.49 |  |  | 0.495 | 176 | 1045.44 | 176 | 1397.93 |  | 1397.93 | 1 | 1
10.13 | Head Teachers for Upper Primary in position (if the number of children exceeds 100 in a school) | 7 | 71.4 | 20.33 | 16.85 | 4 | 37.18 | 57.1429 | 52.0728 |  | 16.85 | 0.935 | 15 | 106.59 | 15 | 123.44 | 0 | 16.85 |  |  | 0.935 | 4 | 44.88 | 4 | 61.73 |  | 61.73 | 1 | 1
10.14 | Part Time Instructors in position |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| (a) Art Education |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| (b) Health and Physical Education |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| (c) Work Education |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 1036 | 5304 | 2984.853 | 1889.43 | 1000 | 4874.283 | 96.5251 | 91.8982 |  | 1889.43 | 2.8 | 1390 | 6771.75 | 1390 | 8661.18 | 0 | 1889.43 |  |  |  | 1000 | 5620.56 | 1000 | 7509.99 |  |  | 1
| Total | 1036 | 5304 | 2984.853 | 1889.43 | 1000 | 4874.283 | 96.5251 | 91.8982 |  | 1889.43 | 2.8 | 1390 | 6771.75 | 1390 | 8661.18 | 0 | 1889.43 |  |  |  | 1000 | 5620.56 | 1000 | 7509.99 |  |  | 1
| Total (New + Existing) | 1036 | 5304 | 2984.853 | 1889.43 | 1000 | 4874.283 | 96.5251 | 91.8982 |  | 1889.43 | 2.8 | 1390 | 6771.75 | 1390 | 8661.18 | 0 | 1889.43 |  |  |  | 1000 | 5620.56 | 1000 | 7509.99 |  |  | 1
11 | Training |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (A) Training of Teachers |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
11.01 | 10 days In-service Teachers' Training |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) Class I & II | 94 | 0.47 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0.01 | 250 | 2.5 | 250 | 2.5 | 0 | 0 |  |  | 0.01 | 250 | 2.5 | 250 | 2.5 | Recommended as proposed (10 days non-residential) | 2.5 | 1 | 1
| (b) Class III to V | 456 | 2.28 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0.01 | 400 | 4 | 400 | 4 | 0 | 0 |  |  | 0.01 | 400 | 4 | 400 | 4 |  | 4 | 1 | 1
| (c) Class VI to VIII | 119 | 0.595 | 0 | 0 |  |  | 0 | 0 |  | 0 | 0.01 | 375 | 3.75 | 375 | 3.75 | 0 | 0 |  |  | 0.01 | 375 | 3.75 | 375 | 3.75 |  | 3.75 | 1 | 1
11.02 | Follow up meetings at CRC level-2 days |  |  | 0 | 0 | [5 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Follow up meetings at CRC level-10 days |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Class I & II | 94 | 0.47 | 0.47 |  | 94 | 0.47 | 100 | 100 |  | 0 | 0.01 | 250 | 2.5 | 250 | 2.5 | 0 | 0 |  |  | 0.01 | 250 | 2.5 | 250 | 2.5 | Recommended as proposed (10 days non-residential) | 2.5 | 1 | 1
| (b) Class III to V | 456 | 2.28 | 2.28 |  | 456 | 2.28 | 100 | 100 |  | 0 | 0.01 | 400 | 4 | 400 | 4 | 0 | 0 |  |  | 0.01 | 400 | 4 | 400 | 4 |  | 4 | 1 | 1
| (c) Class VI to VIII | 119 | 0.595 | 0.595 |  | 119 | 0.595 | 100 | 100 |  | 0 | 0.01 | 375 | 3.75 | 375 | 3.75 | 0 | 0 |  |  | 0.01 | 375 | 3.75 | 375 | 3.75 |  | 3.75 | 1 | 1
11.03 | Induction Training for Newly Recruited Teachers | 900 | 27 | 25.38 |  | 783 | 25.38 | 87 | 94 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
11.04 | Training of untrained Teachers |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Trainng of untrained teachers to acquire professional qualifications over a two year period (Year I) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) Trainng of untrained teachers to acquire professional qualifications over a two year period (Year II) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (B) Training of Resource Persons |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
11.05 | Training for Resource Persons & Master Trainers (this may include BRCCs,BRPs, CRCCs, DIET faculties and any other persons designated as Resource Persons) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (a) Class I & II | 10 | 0.05 | 0.05 |  | 10 | 0.05 | 100 | 100 |  | 0 | 0.01 | 10 | 0.1 | 10 | 0.1 | 0 | 0 |  |  | 0.01 | 10 | 0.1 | 10 | 0.1 | Recommended as proposed (10 days non-residential) | 0.1 | 1 | 1
| (b) Class III to V | 7 | 0.035 | 0.035 |  | 7 | 0.035 | 100 | 100 |  | 0 | 0.01 | 7 | 0.07 | 7 | 0.07 | 0 | 0 |  |  | 0.01 | 7 | 0.07 | 7 | 0.07 |  | 0.07 | 1 | 1
| (c) Class VI to VIII | 4 | 0.02 | 0.02 |  | 4 | 0.02 | 100 | 100 |  | 0 | 0.01 | 4 | 0.04 | 4 | 0.04 | 0 | 0 |  |  | 0.01 | 4 | 0.04 | 4 | 0.04 |  | 0.04 | 1 | 1
| (C) NUEPA School Leadership Programme | 33 | 0.528 | 0.528 |  | 33 | 0.528 | 100 | 100 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
11.06 | Capacity Building of Heads/Resource person & CRC for 10 days |  |  | 0 | [6 empty] | 0 | 0.01 | 21 | 0.21 | 21 | 0.21 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Not Recommended | 0 | 1 | 1
11.07 | Preparation & Printing of Module for Induction Training |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
11.08 | 2 meetings of SRG |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 2292 | 34.323 | 29.358 | 0 | 1506 | 29.358 | 65.7068 | 85.5345 |  | 0 | 0.035 | 2092 | 20.92 | 2092 | 20.92 | 0 | 0 |  |  | 0.035 | 2071 | 20.71 | 2071 | 20.71 |  |  | 1
12 | Academic Support through Block Resource Centre/ URC |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
12.01 | Salary of Faculty and Staff |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a)6 RPs at BRC for subject specific training, | 1 | 5.4 | 3.386 | 1.768 | 1 | 5.154 | 100 | 95.4444 |  | 1.768 | 0.5 | 14 | 84 | 14 | 85.768 | 0 | 1.768 |  |  | 0.495 | 1 | 5.94 | 1 | 7.708 | Recommended as appraised with 10% increment | 7.708 | 1 | 1
| (b) 2 RPs for CWSN | 1 | 5.4 | 3.386 | 1.768 | 1 | 5.154 | 100 | 95.4444 |  | 1.768 | 0.5 | 2 | 12 | 2 | 13.768 | 0 | 1.768 |  |  | 0.495 | 1 | 5.94 | 1 | 7.708 | Recommended as appraised with 10% increment | 7.708 | 1 | 1
| (c) 2 MIS Coordinator |  |  | 0 | [6 empty] | 0 | 0.475 | 2 | 11.4 | 2 | 11.4 | 0 | 0 |  |  | 5.7 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1
| (d) 2 Data Entry Operator in position |  |  | 0 | [6 empty] | 0 | 0.365 | 2 | 8.76 | 2 | 8.76 | 0 | 0 |  |  | 4.38 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1
| (e)2 Accountant-cum-support staff for every 50 schools |  |  | 0 | [6 empty] | 0 | 0.475 | 2 | 5.7 | 2 | 5.7 | 0 | 0 |  |  | 2.85 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1
12.02 | Furniture Grant |  |  | 0 | [6 empty] | 0 | 0.5 | 2 | 1 | 2 | 1 | 0 | 0 |  |  | 0.5 | 0 | 0 | 0 | 0 |  | 0 | 1 | 1
12.03 | Replacement of Funiture Grant (Once in 5 years) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
12.04 | Contingency Grant | 1 | 0.5 | 0.5 |  | 1 | 0.5 | 100 | 100 |  | 0 | 0.5 | 2 | 1 | 2 | 1 | 0 | 0 |  |  | 0.5 | 2 | 1 | 2 | 1 | Recommended as proposed | 1 | 1 | 1
12.05 | Meeting TA (@ Rs. 2500 P.M.) | 1 | 0.3 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0.3 | 2 | 0.6 | 2 | 0.6 | 0 | 0 |  |  | 0.3 | 2 | 0.6 | 2 | 0.6 | Recommended as proposed | 0.6 | 1 | 1
12.06 | TLM Grant |  |  | 0 | [6 empty] | 0 | 0.1 | 2 | 0.2 | 2 | 0.2 | 0 | 0 |  |  | 0.1 |  | 0 | 0 | 0 |  | 0 | 1 | 1
12.07 | Maintenace Grant |  |  | 0 | [6 empty] | 0 | 0.1 | 2 | 0.2 | 2 | 0.2 | 0 | 0 |  |  | 0.1 |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 4 | 11.6 | 7.272 | 3.536 | 3 | 10.808 | 75 | 93.1724 |  | 3.536 |  | 2 | 124.86 | 32 | 128.396 | 0 | 3.536 |  |  |  | 2 | 13.48 | 2 | 17.016 |  |  | 1
13 | Academic Support through Cluster Resource Centres |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
13.01 | Salary, of Cluster Coordinator, full time | 20 | 108 | 68.485 | 34.525 | 20 | 103.01 | 100 | 95.3796 |  | 34.525 | 6 | 20 | 120 | 20 | 154.525 | 0 | 34.525 |  |  | 0.495 | 20 | 118.8 | 20 | 153.325 | Recommended as appraised with 10% increment | 153.325 | 1 | 1
13.02 | Furniture Grant |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
13.03 | Replacement of Funiture Grant (Once in 5 years) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
13.04 | Contingency Grant | 20 | 2 | 2 |  | 20 | 2 | 100 | 100 |  | 0 | 0.1 | 20 | 2 | 20 | 2 | 0 | 0 |  |  | 0.1 | 20 | 2 | 20 | 2 | Recommended as proposed | 2 | 1 | 1
13.05 | Meeting TA | 20 | 2.4 | 2.4 |  | 20 | 2.4 | 100 | 100 |  | 0 | 0.12 | 20 | 2.4 | 20 | 2.4 | 0 | 0 |  |  | 0.12 | 20 | 2.4 | 20 | 2.4 |  | 2.4 | 1 | 1
13.06 | TLM Grant |  |  | 0 | [6 empty] | 0 | 0.03 | 20 | 0.6 | 20 | 0.6 | 0 | 0 |  |  | 0.03 |  | 0 | 0 | 0 |  | 0 | 1 | 1
13.07 | Maintenace Grant |  |  | 0 | [6 empty] | 0 | 0.02 | 20 | 0.4 | 20 | 0.4 | 0 | 0 |  |  | 0.02 |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 20 | 112.4 | 72.885 | 34.525 | 20 | 107.41 | 100 | 95.5605 |  | 34.525 | 0.768 | 20 | 125.4 | 20 | 159.925 | 0 | 34.525 |  |  |  | 20 | 123.2 | 20 | 157.725 |  |  | 1
14 | Computer Aided Education in UPS under Innovation |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
14.01 | Computer Aided Education in Upper Primary Schools (Physical target = No. of schools per district) including RAA |  | 50 | 0.305 | 0.06 | 0 | 0.365 |  | 0.73 | [7 empty] | 0 | [7 empty] | 0 | Recommended as appriased (Rs. 25.00 lakh for CAL in exsiting 16 schools and Rs. 25 lakh fo RAA). Spillover Rs. 0.06 lakh recommended. | 0 | 1 | 1
| (a) Number of districts |  |  | 0 | 0 | [5 empty] | 0.06 | 49.94 | 1 | 49.94 | 1 | 50 | 0 | 0.06 |  |  | 49.94 | 1 | 49.94 | 1 | 50 |  | 50 | 1 | 1
| (b) Number of schools |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total |  | 50 | 0.305 | 0.06 | 0 | 0.365 |  | 0.73 |  | 0.06 | 0 | 1 | 49.94 | 1 | 50 | 0 | 0.06 |  |  | 0 | 1 | 49.94 | 1 | 50 |  |  | 1
15 | Libraries |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
15.01 | Primary |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
15.02 | Upper Primary |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| ANNUAL GRANTS |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
16 | Teachers' Grant |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
16.01 | Primary |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) Class I & II | 788 | 3.94 | 3.94 |  | 788 | 3.94 | 100 | 100 |  | 0 | 0.005 | 674 | 3.37 | 674 | 3.37 | 0 | 0 |  |  | 0.005 | 674 | 3.37 | 674 | 3.37 | Recommended as proposed | 3.37 | 1 | 1
| (b) Class III to V | 1183 | 5.915 | 5.915 |  | 1183 | 5.915 | 100 | 100 |  | 0 | 0.005 | 1014 | 5.07 | 1014 | 5.07 | 0 | 0 |  |  | 0.005 | 1014 | 5.07 | 1014 | 5.07 |  | 5.07 | 1 | 1
16.02 | Upper Primary: Class VI to VIII | 1683 | 8.415 | 8.415 |  | 1683 | 8.415 | 100 | 100 |  | 0 | 0.005 | 2487 | 12.435 | 2487 | 12.435 | 0 | 0 |  |  | 0.005 | 2487 | 12.435 | 2487 | 12.435 |  | 12.435 | 1 | 1
| Sub Total | 3654 | 18.27 | 18.27 |  | 3654 | 18.27 | 100 | 100 |  | 0 | 0.015 | 4175 | 20.875 | 4175 | 20.875 | 0 | 0 |  |  |  | 4175 | 20.875 | 4175 | 20.875 |  |  | 1
17 | School Grant |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
17.01 | Primary | 117 | 5.85 | 5.85 |  | 117 | 5.85 | 100 | 100 |  | 0 | 0.05 | 119 | 5.95 | 119 | 5.95 | 0 | 0 |  |  | 0.05 | 119 | 5.95 | 119 | 5.95 | Recommended as proposed | 5.95 | 1 | 1
17.02 | Upper Primary | 111 | 7.77 | 7.77 |  | 111 | 7.77 | 100 | 100 |  | 0 | 0.07 | 113 | 7.91 | 113 | 7.91 | 0 | 0 |  |  | 0.07 | 113 | 7.91 | 113 | 7.91 |  | 7.91 | 1 | 1
| Sub Total | 228 | 13.62 | 13.62 |  | 228 | 13.62 | 100 | 100 |  | 0 | 0.12 | 232 | 13.86 | 232 | 13.86 | 0 | 0 |  |  |  | 232 | 13.86 | 232 | 13.86 |  |  | 1
18 | Research, Evaluation, Monitoring & Supervision |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
18.01 | REMS activities | [25 empty] | 0 | 1 | 1
18.02 | Monitoring & Supervision& EMIS |  |  | 0 | [6 empty] | 0 |  |  | 30.65 | 0 | 30.65 | 0 | 0 | [5 empty] | 0 | 0 | Included in above | 0 | 1 | 1
18.03 | SLAS |  |  | 0 | [6 empty] | 0 | 0.14286 | 70 | 10 | 70 | 10 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| Sub Total | 0 | 0 | 0 | 0 |  | 0 |  |  |  | 0 | 0.14286 | 70 | 40.65 | 70 | 40.65 | 0 | 0 |  |  |  | 0 |  |  |  |  | 0 | 1 | 1
19 | Maintenance Grant |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
19.01 | Maintenance Grant ( PS & UPS) | 228 | 17.1 | 17.08 | 0 | 228 | 17.08 | 100 | 99.883 |  | 0 | 0.075 | 232 | 17.4 | 232 | 17.4 | 0 | 0 |  |  | 0.075 | 232 | 17.4 | 232 | 17.4 | Recommended as proposed | 17.4 | 1 | 1
10 | Sub Total | 228 | 17.1 | 17.08 | 0 | 228 | 17.08 | 100 | 99.883 |  | 0 | 0.075 | 232 | 17.4 | 232 | 17.4 | 0 | 0 |  |  |  | 232 | 17.4 | 232 | 17.4 |  |  | 1
20 | Interventions for CWSN |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
20.01 | Provision for Inclusive Education | 2980 | 89.4 | 72.649 | 12.061 | 3555 | 84.71 | 119.2953 | 94.7539 |  | 12.061 | 0.03 | 3552 | 106.56 | 3552 | 118.621 | 0 | 12.061 |  |  | 0.03 | 2933 | 87.99 | 2933 | 100.051 | Recommended as appraised | 100.051 | 1 | 1
| Sub Total | 2980 | 89.4 | 72.649 | 12.061 | 3555 | 84.71 | 119.2953 | 94.7539 |  | 12.061 | 0.03 | 3552 | 106.56 | 3552 | 118.621 | 0 | 12.061 |  |  |  | 2933 | 87.99 | 2933 | 100.051 |  |  | 1
21 | Innovation Head up to Rs. 50 lakh per district |  |  | 0 | [6 empty] | 0 | [5 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
21.01 | Girls Education |  | 12.5 | 0 |  |  |  |  | 0 |  | 0 | 0.11636 | 44 | 5.12 | 44 | 5.12 | 0 | 0 |  |  | 12.5 | 1 | 12.5 | 1 | 12.5 | This amount include 15 lakh under innovation for C-NAS | 12.5 | 1 | 1
21.02 | Intervention for SC / ST children |  | 12.5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 12.5 | 1 | 12.5 | 1 | 12.5 |  | 12.5 | 1 | 1
21.03 | Intervention for Minority Community children |  | 12.5 | 0 |  |  |  |  | 0 |  | 0 |  |  |  | 0 | 0 | 0 | 0 |  |  | 12.5 | 1 | 12.5 | 1 | 12.5 |  | 12.5 | 1 | 1
21.04 | Intervention for Urban Deprived children |  | 12.5 | 0.6 | 2.81 |  | 3.41 |  | 27.28 |  | 2.81 |  |  |  | 0 | 2.81 | 0 | 2.81 |  |  | 9.69 | 1 | 9.69 | 1 | 12.5 |  | 12.5 | 1 | 1
21.05 | Padhe Bharat Bhadhe Bharat |  |  | 0 | [6 empty] | 0 | 0.3364 | 113 | 38.013 | 113 | 38.013 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
21.06 | Rashtriya Aviskar Abhiyan- |  |  | 0 | [6 empty] | 0 | 0.17162 | 40 | 6.865 | 40 | 6.865 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| Sub Total |  | 50 | 0.6 | 2.81 |  | 3.41 |  | 6.82 |  | 2.81 | 0.62439 | 197 | 49.998 | 197 | 52.808 | 0 | 2.81 |  |  |  | 1 | 47.19 | 1 | 50 |  |  | 1
22 | SMC/PRI Training |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
22.01 | Residential (3 days) | 672 | 2.016 | 1.95 |  | 672 | 1.95 | 100 | 96.7262 |  | 0 | 0.003 | 1428 | 4.284 | 1428 | 4.284 | 0 | 0 |  |  | 0.003 | 684 | 2.052 | 684 | 2.052 | Recommended as appraised | 2.052 | 1 | 1
22.02 | Non-residential (3 days) |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| Sub Total | 672 | 2.016 | 1.95 |  | 672 | 1.95 | 100 | 96.7262 |  | 0 | 0.003 | 1428 | 4.284 | 1428 | 4.284 | 0 | 0 |  |  |  | 684 | 2.052 | 684 | 2.052 |  |  | 1
VI | SCHOOL INFRASTRUCTURE |  |  | 0 | [12 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
23 | Civil Works Construction |  |  | 0 | [12 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
23.01 | New Primary School (Rural) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.02 | New Primary School (Urban) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.03 | New Upper Primary (Rural) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.04 | New Upper Primary (Urban) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.05 | ACR in lieu of upgraded Upper Primary School |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.06 | Additional Class Room (Rural) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.07 | Additional Class Room (Urban) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.08 | Additional Class Room (Hill Area) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.09 | Additional Class Room (Plain Area) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.1 | Boys Toilet |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.11 | Separate Girls Toilet |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.12 | CWSN Friendly Toilets |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.13 | Drinking Water Facility |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.14 | Boundary Wall |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.15 | URC-rooms | 0 | 16 | 0 |  |  |  |  | 0 | 2 | 16 |  |  |  | 2 | 16 | 2 | 16 |  |  |  |  | 0 | 2 | 16 | Recommnded as proposed | 16 | 1 | 1
23.16 | Office-cum-store-cum-Head Teacher's room (Primary) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.17 | Office-cum-store-cum-Head Teacher's room (Upper Primary) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.18 | Augumentation of training facility in BRC (one time) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.19 | Ramps with Handrails |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.2 | Handrails in existing ramps |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.21 | Furniture for Govt. UPS (per child) |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.22 | Major Repairs for Primary School |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.23 | Major Repairs for Upper Primary School |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.24 | Residential Schools/hostels for specific category of children |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.25 | (a) Construction of Building including boundary wall, Water and sanitation facilities, electric installation |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.26 | (b) Construction of residential hostel |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.27 | (c) Refurbishing unused old buildings |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.28 | (d) Construction of Hostel in existing Govt UPS |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
23.29 | Others Bala grant | 3 | 6 | 4 | 2 | 3 | 6 | 100 | 100 | 0 | 2 | 2 | 2 | 4 | 2 | 6 | 0 | 2 |  |  |  |  | 0 | 0 | 2 | Spillover recommended as proposed | 2 | 1 | 1
23.3 | Maintenance of BaLA project |  |  | 0 | [7 empty] | 0.5 | 38 | 19 | 38 | 19 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Not Recommended | 0 | 1 | 1
| Sub Total |  | 22 | 4 | 2 |  | 6 |  | 27.2727 | 2 | 18 | 2.5 | 40 | 23 | 42 | 41 | 2 | 18 |  |  |  | 0 | 0 | 2 | 18 |  |  | 1 | 1
24 | PROJECT MANAGEMENT COST |  |  | 0 | [12 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
24.01 | Management |  |  | 0 | [12 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
24.01 | Management up to 3.5% |  | 196.36 | 88.801 | 50.199 |  | 139 |  | 70.7883 |  | 50.199 |  |  | 288.57 | 0 | 338.769 | 0 | 50.199 |  |  |  |  | 240 | 0 | 290.199 |  | 290.199 | 1
| (a) Project Management and MIS |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [8 empty] | 0 | 1 | 1
| (b) Training of Educational Administrators |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| (c) School Mapping and Social Mapping |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 |  | 0 | 1 | 1
| Sub Total |  | 196.36 | 88.801 | 50.199 |  | 139 |  | 70.7883 |  | 50.199 |  |  | 288.57 | 0 | 338.769 | 0 | 50.199 |  |  |  |  | 240 | 0 | 290.199 |  |  | 1
24.02 | Learning Enhancement Programme (LEP) only for Large Scale Integrated Programmes for Quality Improvement (up to 2%) |  |  | 0 | [12 empty] | 0 | 0 | [8 empty] | 0 | 1 | 1
| (a) Class I & II |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 1 | 1
| (b) Class III to V |  | 42.488 | 42.49 |  |  | 42.49 |  | 100.0047 |  | 0 |  |  | 5.65 | 0 | 5.65 | 0 | 0 |  |  |  |  | 5.65 | 0 | 5.65 |  | 5.65 | 1
| (c) Class VI to VIII |  | 88 | 65.08 |  |  | 65.08 |  | 73.9545 |  | 0 |  |  | 136.535 | 0 | 136.535 | 0 | 0 |  |  |  |  | 130 | 0 | 130 | Recommended as appriased | 130 | 1
24.03 | Community Mobilization activities (up to 0.5%) |  | 22 | 8.16 | 1.08 |  | 9.24 |  | 42 |  | 1.08 |  |  | 35 | 0 | 36.08 | 0 | 1.08 |  |  |  |  | 22 | 0 | 23.08 | Recommended as appraised | 23.08 | 1
| Sub Total |  | 152.488 | 115.73 | 1.08 |  | 116.81 |  | 76.6027 | 0 | 1.08 |  |  | 177.185 | 0 | 178.265 | 0 | 1.08 |  |  |  |  | 157.65 | 0 | 158.73 |  |  | 1
| Total of SSA (District) | 124855 | 6554.406 | 3610.818 | 2282.451 | 124445 | 5893.269 |  | 89.9131 |  | 2298.451 |  |  | 8484.653 |  | 10783.104 |  | 2298.451 | 0 | 0 |  |  | 7078.963 |  | 9377.414 |  | 9377.414 | 1
25 | STATE COMPONENT |  |  | 0 | [12 empty] | 0 | 0 | [9 empty] | 1 | 1
25.01 | Management & MIS |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0 | [9 empty] | 1 | 1
25.02 | REMS | 228 | 3.414 | 1.78 | 0.3 |  | 2.08 | 0 | 60.9256 |  | 0.3 |  |  | 1.66 | 0 | 1.96 | 0 | 0.3 |  |  |  | 288 | 3.42 | 288 | 3.72 | Recommended as appraised. Also Recommended Rs. 15.00 lakh for C-NAS to be booked under innovation
| Sub Total | 228 | 3.414 | 1.78 | 0.3 | 0 | 2.08 | 0 | 60.9256 | 0 | 0.3 | 0 | 0 | 1.66 | 0 | 1.96 | 0 | 0.3 | 0 | 0 | 0 | 288 | 3.42 | 288 | 3.72 |  |  | 1 | 0
| STATE SSA TOTAL |  | 6557.82 | 3612.598 | 2282.751 |  | 5895.349 | 0 | 89.898 | 0 | 2298.751 | 0 | 0 | 8486.313 | 0 | 10785.064 | 0 | 2298.751 | 0 | 0 | 0 |  | 7082.383 |  | 9381.134 |  |  | 1 | 0
26 | KGBV Financial Provision | [26 empty] | 1 | 1
| Sub Total | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | [6 empty] | 1 | 1 |  |  | -9377.414
| STATE SSA TOTAL | 0 | 6557.82 | 3612.598 | 2282.751 | 0 | 5895.349 | 0 | 89.898 | 0 | 2298.751 | 0 | 0 | 8486.313 | 0 | 10785.064 | 0 | 2298.751 | 0 | 0 | 0 | 0 | 7082.383 | 0 | 9381.134 |  | 9381.134
[16 empty] | 10785.064 | [8 empty] | 9381.134
[26 empty] | Management Cost (3.5%) |  |  |  |  | 3.0934
[26 empty] | Learning Enhancement Prog (2%) |  |  |  |  | 1.446
[26 empty] | Community Mobilisation (0.5%) |  |  |  |  | 0.24603
[26 empty] | Total Mgt. Cost (Mgt + LEP + Com Mob) 6% |  |  |  |  | 4.7854
[26 empty] | Civil Work (33%) |  |  |  |  | 0.19187

## Exe-Sum
(V) | Provision for 2017-18:
(Rs. in lakh)
| Outlay approved | Capital Head (all civil works under SSA & KGBV) | General Head | FC Award | Net General Head | GOI Share (100%)
[6 empty] | Capital Head | General Head | Total
| 9381.134 | 18 | 9363.134 | 0 | 9363.134 | 18 | 9363.134 | 9381.134
(VI) | Total Recommended Budget for 2017-18:
(Rs. in lakh)
| S. No. | Head | Outlay Proposed |  |  | Approved Outlay
|  |  | Spill Over | Fresh | Total | Spill Over | Fresh | Total
| 1 | SSA | 2298.751 | 8486.313 | 10785.064 | 2298.751 | 7082.383 | 9381.134
| 2 | KGBV | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 2298.751 | 8486.313 | 10785.064 | 2298.751 | 7082.383 | 9381.134
(VII) | Break up of Interventions:
(Rs. in lakh)
|  | SNo. | Category |  |  |  | Financial Recommendation for 2017-18 | % | Financial Recommendation for 2016-17 | %
Access & Retention
|  | 1 | Transport/Escort Facility |  |  |  | 0 | 0 |  | 0
|  | 2 | Uniforms |  |  |  | 210.36 | 2.2424 | 0 | 0
|  | 3 | Residential Schools |  |  |  | 0 | 0 | 0 | 0
|  | 4 | Residential Hostels |  |  |  |  | 0 | 0 | 0
|  |  | Sub Total |  |  |  | 210.36 | 2.2424 | 0 | 0
Quality
|  | 5 | Teacher's Salary |  |  |  | 7509.99 | 80.0542 | 5304 | 56.539
|  | 6 | Salary of Resource Teachers under CWSN |  |  |  | 0 | 0 | 0 | 0
|  | 7 | Textbooks |  |  |  | 417.426 | 4.4496 | 209.959 | 2.2381
|  | 8 | Special training |  |  |  | 323.02 | 3.4433 | 270.87 | 2.8874
|  | 9 | LEP |  |  |  | 135.65 | 1.446 | 130.488 | 1.391
|  | 10 | Teachers’ Training |  |  |  | 20.71 | 0.22076 | 34.323 | 0.36587
|  | 11 | Teachers' Training under CWSN |  |  |  | 0 | 0 | 0 | 0
|  | 12 | BRC/URC |  |  |  | 17.016 | 0.18139 | 11.6 | 0.12365
|  | 13 | CRC |  |  |  | 157.725 | 1.6813 | 112.4 | 1.1981
|  | 14 | TLE for new schools |  |  |  | 0 | 0 | 0 | 0
|  | 15 | Teachers Grant |  |  |  | 20.875 | 0.22252 | 18.27 | 0.19475
|  | 16 | School Grant |  |  |  | 13.86 | 0.14774 | 13.62 | 0.14519
|  | 17 | REMS |  |  |  | 3.72 | 0.039654 | 3.414 | 0.036392
|  | 18 | Innovative Activities |  |  |  | 50 | 0.53298 | 50 | 0.53298
|  | 19 | Libraries in schools |  |  |  | 0 | 0 | 0 | 0
|  | 20 | Innovation for CAL |  |  |  | 50 | 0.53298 | 50 | 0.53298
|  |  | Sub Total |  |  |  | 8719.992 | 92.9524 | 6208.944 | 66.1854
Equity
|  | 21 | IE |  |  |  | 100.051 | 1.0665 | 89.4 | 0.95298
|  | 22 | Community Mobilization |  |  |  | 23.08 | 0.24603 | 22 | 0.23451
|  | 23 | SMC/PRI Training |  |  |  | 2.052 | 0.021874 | 2.016 | 0.02149
|  |  | Sub Total |  |  |  | 125.183 | 1.3344 | 113.416 | 1.209
Infrastructure Development
|  | 24 | Civil Works |  |  |  | 18 | 0.19187 | 22 | 0.23451
|  | 25 | Maintenance Grant |  |  |  | 17.4 | 0.18548 | 17.1 | 0.18228
|  |  | Sub Total |  |  |  | 35.4 | 0.37735 | 39.1 | 0.41679
|  | 26 | Programme Management |  |  |  | 290.199 | 3.0934 | 196.36 | 2.0931
|  |  | Sub Total |  |  |  | 290.199 | 3.0934 | 196.36 | 2.0931
|  | 27 | Reimbursement of Fee against 25% admission under Section 12(1)(c) of RTE Act 2009 (Entry Level) subject to upper limit of 20% of AWP&B guidelines issued by MHRD |  |  |  | 0 | 0 | 0 | 0
|  |  | Sub Total |  |  |  | 9381.134 | 100 | 6557.82 | 69.9043
Gender
|  | 28 | KGBV |  |  |  | 0 | 0 | 0 | 0
|  |  | Sub Total |  |  |  | 0 | 0 | 0 | 0
|  |  | TOTAL |  |  |  | 9381.134 | 100 | 6557.82 | 69.9043

## Categorywise
State: Chandigarh UT | [11 empty] | (Rs. in lakh
Proposal & Recommendations for AWP&B 2017-18
State: |  | Proposed by State for 2017-2018 |  |  |  |  | Recommendation for 2017-2018 |  |  |  |  | Remarks
S.No. | Intervention | Spill over | Fresh Proposal |  | Total |  | Spill over | Fresh Recommended |  | Total
|  | Fin. | Phy. | Fin | Phy. | Fin | Fin. | Phy. | Fin | Phy. | Fin
Category 1
1 | Reimbursement under Section 12(1)(c)
2 | Free Text Books
| a. Primary | 92.37 | 60225 | 90.3375 | 60225 | 182.7075 | 92.37 | 60225 | 90.3375 | 60225 | 182.7075 | Recommended as proposed | 1
| b. Upper Primary | 117.39 | 46858 | 117.145 | 46858 | 234.535 | 117.39 | 46858 | 117.145 | 46858 | 234.535 | Recommended as proposed | 1
| c. Large Print Book | 0 | 80 | 0.174 | 80 | 0.174 | 0 | 80 | 0.174 | 80 | 0.174 | Recommended as proposed | 1
| d. Braille Book | 0 | 5 | 0.0095 | 5 | 0.0095 | 0 | 5 | 0.0095 | 5 | 0.0095 | Recommended as proposed | 1
3 | Free Uniform | 0 | 52590 | 184.065 | 52590 | 184.065 | 0 | 52590 | 210.36 | 52590 | 210.36 | Not Recommended as the UT wants direct transfer of funds which is not permissible under SSA Norms | 0
4 | Residential School/ Hostel | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 1
5 | KGBV | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 1
6 | IE | 12.061 | 3552 | 106.56 | 3552 | 118.621 | 12.061 | 2933 | 87.99 | 2933 | 100.051 | Recommended as appraised | 0
7 | School Grant | 0 | 232 | 13.86 | 232 | 13.86 | 0 | 232 | 13.86 | 232 | 13.86 | Recommended as proposed | 1
8 | Maintenance Grant | 0 | 232 | 17.4 | 232 | 17.4 | 0 | 232 | 17.4 | 232 | 17.4 | Recommended as proposed | 1
9 | Major Repairs | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 1
10 | a. Project Management | 50.199 | 0 | 288.57 | 0 | 338.769 | 50.199 | 0 | 240 | 0 | 290.199 | Recommended as appraised | 0
| b. Finance | Covered Under Project Management and Overall allocation | [10 empty] | 1
Sub Total |  | 272.02 | 163774 | 818.121 | 163774 | 1090.141 | 272.02 | 163155 | 777.276 | 163155 | 1049.296 | 11.1852 | 0
Category 2 | [12 empty] | 1
11 | Transport / Escort facility |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  | 1
12 | Special Training for Age appropriate addmission of OoSC |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| Residential (Fresh) |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (a) 12 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (b) 9 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (c) 6 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (d) 3 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| Residential continuing from previous year |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (a) 12 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (b) 9 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (c) 6 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (d) 3 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| Non Residential (Fresh) |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (a) 12 months | 47.11 | 2629 | 157.74 | 2629 | 204.85 | 47.11 | 2629 | 157.74 | 2629 | 204.85 | Recommended as proposed | 1
| (b) 9 months | 4.02 | 299 | 13.455 | 299 | 17.475 | 4.02 | 299 | 13.455 | 299 | 17.475 | Recommended as proposed | 1
| (c) 6 months | 2.46 | 274 | 8.22 | 274 | 10.68 | 2.46 | 274 | 8.22 | 274 | 10.68 | Recommended as proposed | 1
| (d) 3 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| NonResidential continuing from previous year |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (a) 12 months | 9.18 | 512 | 30.72 | 512 | 39.9 | 9.18 | 512 | 30.72 | 512 | 39.9 | Recommended as proposed | 1
| (b) 9 months | 4.48 | 333 | 14.985 | 333 | 19.465 | 4.48 | 333 | 14.985 | 333 | 19.465 | Recommended as proposed | 1
| (c) 6 months | 2.3 | 257 | 7.71 | 257 | 10.01 | 2.3 | 257 | 7.71 | 257 | 10.01 | Recommended as proposed | 1
| (d) 3 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| Madarasa/Maktab |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (a) 12 months | 7.44 | 414 | 24.84 | 414 | 32.28 | 7.44 | 220 | 13.2 | 220 | 20.64 | Recommended as appraised. Includes 124 continuing and 96 Fresh @ of Rs. 0.06 lakh each | 0
| (b) 9 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (c) 6 months (seasonal hostel) |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (d) 3 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| Seasonal Hostel (Non Residential) |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (a) 12 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (b) 9 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (c) 6 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
| (d) 3 months |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
13 | Teacher Training | 0 | 2092 | 20.92 | 2092 | 20.92 | 0 | 2071 | 20.71 | 2071 | 20.71 | Recommended as proposed | 0
14 | Academic Support through BRC/CRC | [9 empty] | 0 |  | 1
| a) BRC | 3.536 | 32 | 124.86 | 32 | 128.396 | 3.536 | 2 | 13.48 | 2 | 17.016 | Recommended as appraised | 0
| b) CRC | 34.525 | 20 | 125.4 | 20 | 159.925 | 34.525 | 20 | 123.2 | 20 | 157.725 | Recommended as appraised | 0
15 | Learning Enhancement Programme (LEP) | 0 | 0 | 142.185 | 0 | 142.185 | 0 | 0 | 135.65 | 0 | 135.65 | Recommended as appraised | 0
16 | a. Innovation fund for CAL | 0.06 | 1 | 49.94 | 1 | 50 | 0.06 | 1 | 49.94 | 1 | 50 | Recommended as appriased (Rs. 25.00 lakh for CAL in exsiting 16 schools and Rs. 25 lakh fo RAA). Spillover Rs. 0.06 lakh recommended. | 1
| b. Rashtriya Avishkar Abhiyan (RAA) | This activity will be supported under CAL | [10 empty] | 1
17 | Library | [9 empty] | 0 |  | 1
18 | Teacher Grant | 0 | 4175 | 20.875 | 4175 | 20.875 | 0 | 4175 | 20.875 | 4175 | 20.875 | Recommended as proposed | 1
19 | TLE for New Schools |  |  |  | 0 | 0 |  |  |  |  | 0 |  | 1
20 | REMS | 0.3 | 70 | 42.31 | 70 | 42.61 | 0.3 | 288 | 3.42 | 288 | 3.72 | Recommended as appraised. Besides, recommended Rs. 15.00 lakh for C-NAS to be booked under innovation | 0
21 | a. Innovation | 2.81 | 197 | 49.998 | 197 | 52.808 | 2.81 | 1 | 47.19 | 1 | 50 | Recommended as appraised. Includes Rs. 15.00 lakh for C-NAS to be booked under innovation | 0
| b. Pade Bharat Bade Bharat (PBBB) | This activity will be supported under Innovation Head | [10 empty] | 1
22 | Community Mobilization (0.5%) | 1.08 | 0 | 35 | 0 | 36.08 | 1.08 | 0 | 22 | 0 | 23.08 |  | 0
23 | SMC Training | 0 | 1428 | 4.284 | 1428 | 4.284 | 0 | 684 | 2.052 | 684 | 2.052 | Recommended as appraised | 0
Total |  | 119.301 | 12733 | 873.442 | 12733 | 992.743 | 119.301 | 11766 | 684.547 | 11766 | 803.848 | 8.5688 | 0
Category 3 | [12 empty] | 1
24 | Teacher Salary | 1889.43 | 1390 | 6771.75 | 1390 | 8661.18 | 1889.43 | 1000 | 5620.56 | 1000 | 7509.99 | Recommended as appraised. Spill over of Rs.2282.75 lakh recommended to repay the loan taken to conduct the activities. | 0
25 | New Schools (Building) | [11 empty] | 1
26 | Additional Classrooms (ACR) | [10 empty] | Recommended as proposed | 1
27 | Block Resource Centers | [11 empty] | 1
28 | Cluster Resource Centers | [11 empty] | 1
29 | Residential Schools (Construction Building) | [11 empty] | 1
30 | Toilets & Drinking Water | [11 empty] | 1
31 | Furniture | [11 empty] | 1
32 | Civil Works | [11 empty] | 1
| a. Boundary Walls | [11 empty] | 1
| b. Ramps | [11 empty] | 1
| Others | 18 | 40 | 23 | 40 | 41 | 18 |  | 0 |  | 18
33 | Repairs to School Buildings | [11 empty] | 1
34 | a. Maintenance Grant | [11 empty] | 1
34 | b. Swacchh Vidyalaya | [11 empty] | 1
35 | School and Social Mapping: | [11 empty] | 1
36 | Opening new Primary Schools: | [11 empty] | 1
37 | Opening Upper Primary Schools/Sections: | [11 empty] | 1
38 | Conversion of EGS Centres into schools: | All EGS already converted into Schools | [10 empty] | 1
39 | SIEMAT | One Time Grant | [10 empty] | 1
40 | NPGEL | Activity Closed | [10 empty] | 1
| Total | 1907.43 |  | 6794.75 |  | 8702.18 | 1907.43 |  | 5620.56 |  | 7527.99 | 80.2461 | 0
| Grand Total | 2298.751 |  | 8486.313 |  | 10785.064 | 2298.751 |  | 7082.383 |  | 9381.134
|  | 2298.751 |  | 8486.313 |  | 10785.064 | 2298.751 |  | 7082.383 |  | 9381.134
|  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
?

## Fund released-2016-17
Fund released 2016-17 & Recommended outlay 2017-18 SSA, Andaman & Nicobar Islands
S. No. | Particulars | Amount Rs. in Crore | Amount Rs. in Lakh
1 | Approved outlay for the year 2016-17 | 65.5782 | 6557.82
2 | Opening balance with State as on 01/04/2016 | 1.4 | 140
3 | Actual outlay size (after deducting opening bal.) | 64.1782 | 6417.82
4 | GOI Share of outlay as per sharing pattern (100%) | 64.1782 | 6417.82
Status of GOI releases during 2016-17
| Adhoc Funds (Released) | 8.452 | 100
| Balance of 1st installment (Released) | 24.34 | 259
| 2nd installment (Released) | 0.55
| Total Releases | 33.342 | 359
7 | Current year’s proposal (2017-18) | 107.8506 | 10785.064
8 | Current year’s recommendations (2017-18) | 93.8113 | 9381.134
| GOI Share of current year's recommendation | 93.8113 | 9381.134
| Category-I (10.49) - GOI 10.49 (100%) |  | 1049.296
| Category-II (8.04) - GOI 8.04 (100%) |  | 803.848
| Total Category I & II (18.53) GOI (100%) |  | 1853.144
9 | Additional fund allocated as per 14th Finance Commission in 2015-16 and 2016-17

## Sheet1
209.76 | 207.666 | 417.426 | 417.426
| 210.36 | 210.36 | 210.36
| 13.86 | 13.86 | 13.86
| 17.4 | 17.4 | 17.4
12.06 | 87.99 | 100.05 | 100.051
50.199 | 240 | 290.199 | 290.199
| 20.71 | 20.71 | 20.71
| 135.65 | 135.65 | 135.65
0.06 | 49.94 | 50 | 50
| 20.875 | 20.875 | 20.875
2.81 | 47.19 | 50 | 50
0.3 | 3.42 | 3.72 | 3.72
1.08 | 22 | 23.08 | 23.08
| 2.052 | 2.052 | 2.052
76.99 | 246.03 | 323.02 | 323.02
3.54 | 13.48 | 17.02 | 17.016
34.53 | 123.2 | 157.73 | 157.725
18 |  | 18 | 18
1889.43 | 5620.56 | 7509.99 | 7509.99
2298.759 | 7082.383 | 9381.142 | 9381.134